# Multi-Agent Custom Automation Engine: Refactored (Reuse) Deployment Runbook

End-to-end record of how the Multi-Agent Custom Automation Engine (MACAE) accelerator was deployed into the RPSI landing zone by reusing existing shared infrastructure and deploying only the new resources the solution needs, and how every blocker encountered along the way was resolved to reach a fully working application (agent teams load, task submission generates a plan, agents execute and results persist).

Status: COMPLETE application working end-to-end (five agent teams load in the UI, a submitted task passes the responsible-AI check, an orchestration plan is generated, the specialized agents run, and plan/step history persists in Cosmos DB).

This document captures, in sequence: what was reused vs. newly created, the infra modules used, the roles the managed identity holds and why, how authentication was done, which services were used for scripts and frontend execution, the exact commands run, and every blocker with its resolution.

# Current State and Open Points

# Current state:

# - Solution is working end-to-end.

# - All five agent teams (HR, Marketing, RFP Analysis, Contract Compliance, Retail) load and are selectable.

# - Task submission generates an orchestration plan; agents execute and plan/step history persists in Cosmos DB.

# Open points that are still blockers for hardening:

# - Corporate DNS forwarders for private endpoint zones are pending due to DNS freeze.

# - ACR private-only hardening is pending DNS record setup for privatelink.azurecr.io.

# Temporary workarounds currently in use:

# - Backend uses startup /etc/hosts injection (EXTRA_HOSTS) for Cosmos DB and Foundry private endpoint name resolution.

# - UI validation is done from the VM because laptop DNS does not resolve the private Container Apps domain.

# - ACR is left publicly reachable in dev until the DNS freeze is lifted and private DNS records are added.

## 1. Goals & constraints

| Constraint | Decision |
| --- | --- |
| Do not create new networking, Foundry, Search, Cosmos, or Storage | Reuse existing landing-zone resources |
| Deploy the three application tiers (frontend, backend, MCP tool server) | Deploy as Azure Container Apps into the existing internal Container Apps Environment |
| Landing zone is private (internal CAE, private endpoints, no public ingress) | App reachable only inside the VNet; data-load and validation run from an in-VNet VM |
| mg-amcor governance (Deny Public Access, Deny VNet writes) | Scripts must not flip public network access; VNet DNS cannot be changed |
| Least-privilege identity | Reuse the existing user-assigned identity; grant only the data-plane roles the app needs |

### Environment identifiers

| Item | Value |
| --- | --- |
| Subscription | cf397678-b660-4714-bea3-5e5b7748bce2 (rpsi-cloudsolutions-01) |
| Tenant | fe9c207f-da30-4226-82b5-bff6ef031c8c |
| Region | West Europe |
| Deployment RG (new resources) | rg-gen-digitalmfg-rpsi-dev-weu-01 |
| Core landing-zone RG | rg-core-foundry-rpsi-dev-weu-01 |
| Deploy operator (laptop) | (objectId 3984dd78-1262-4920-9c19-f8ea23ff78aa) |
| Solution tag / use case | digitalmfg-reuse / multi-agent-automation |

### Two-plane execution model

Because the landing zone is private, work was split across two machines:

| Machine | Role | Auth | What it did |
| --- | --- | --- | --- |
| Laptop (PowerShell) | Management plane | az login (interactive) | Bicep deploy, ACR build, container app config, RBAC and network inspection |
| VM vm-cm02avdd0007 (PowerShell 5.1) | Data plane + validation | az login --identity (UAI) | Ran the post-deploy data loader (team configs, blob upload, search indexing), browsed the private app URL |

The laptop cannot resolve *.azurecontainerapps.io (corp DNS returns NXDOMAIN), so all UI validation was done from the VM browser, which has hosts-file entries for the private IPs.

## 2. Resources REUSED (existing, not recreated)

| Service | Resource | Resource group | Key network fact |
| --- | --- | --- | --- |
| VNet | vnet-aifoundry-rpsi-dev-weu-01 (10.22.144.0/24) | rg-core-foundry | Custom DNS 10.22.4.4/5, 10.21.4.4/5 (corp) |
| Subnets | snet-cae (/27, delegated Microsoft.App/environments), snet-pe (/27), snet-ai (/25) | rg-core-foundry | CAE subnet cannot host private endpoints |
| Container Apps Environment | cae-foundry-rpsi-dev-weu-01 (internal, static IP 10.22.144.170) | rg-core-foundry | App-to-app traffic resolves to env LB 10.22.144.170 |
| AI Foundry | aif-foundry-rpsi-dev-weu-01 + project DigitalManufacturing | rg-core-foundry | publicNetworkAccess=Enabled, defaultAction=Deny; account-PE FQDNs on .136/.137/.138 |
| Model deployments | gpt-5-mini, gpt-5-chat, gpt-5.5, text-embedding-3-large | rg-core-foundry | Agents + reasoning use gpt-5-mini; responsible-AI check uses gpt-5-chat |
| AI Search | srch-foundry-rpsi-dev-weu-01 (connection srchfoundryrpsidevweuz7toiu) | rg-core-foundry | PE 10.22.144.133; hosts the RAG indexes for the agent teams |
| Cosmos DB | cosmos-foundry-rpsi-dev-weu-01 | rg-core-foundry | publicNetworkAccess=Disabled; PE 10.22.144.134/.135 |
| Storage | stfoundryrpsidweu01 (public Disabled + Deny) | rg-core-foundry | blob-PE 10.22.144.132; holds the dataset blobs indexed into Search |
| Container Registry | acrdigitalmfgrpsidweu01 (Premium) | rg-gen-digitalmfg | Reused for the MACAE images |
| User-Assigned Identity | uai-aci-pull-digitalmfg-rpsi-dev-weu-01 (clientId 38ab20d0-2349-4503-b63a-4152af0b90ed, principalId 5729970b-6f81-4dd9-996b-4f433369aaab) | rg-gen-digitalmfg | The identity the backend and MCP apps authenticate as |
| Bastion VM | vm-cm02avdd0007 (Windows 11 Enterprise multi-session / AVD), IP 10.22.120.68, subnet snet-vm (vnet-shared) | rg-gen-digitalmfg | Data-load + validation host |

## 3. Resources DEPLOYED (new)

| New resource | Type | Where | Notes |
| --- | --- | --- | --- |
| ca-macae-be-rpsi-dev-weu-01 | Container App (backend) | existing CAE | Image acrdigitalmfgrpsidweu01.azurecr.io/macae-backend:reuse-4, port 8000, internal ingress, UAI-authenticated, uvicorn app:app |
| ca-macae-mcp-rpsi-dev-weu-01 | Container App (MCP tool server) | existing CAE | Image acrdigitalmfgrpsidweu01.azurecr.io/macae-mcp:reuse-2, port 9000, internal ingress |
| ca-macae-fe-rpsi-dev-weu-01 | Container App (frontend) | existing CAE | Image acrdigitalmfgrpsidweu01.azurecr.io/macae-frontend:reuse-1, external ingress (browser-facing), proxies /api/* to the internal backend |
| macae (database) + memory (container) | Cosmos DB objects | cosmos-foundry (reused account) | Partition key /session_id; stores plans, steps and agent/step history |

## 4. Roles: what, where, and why

### 4a. Deploy operator (laptop): control plane

| Role | Scope (RG) | Why |
| --- | --- | --- |
| Contributor + User Access Administrator | rg-gen-digitalmfg | Create Container Apps + Cosmos objects; assign roles |
| Contributor + User Access Administrator | rg-core-foundry | Cross-RG create the Cosmos database/container; assign the backend data roles; inspect network settings |
| Virtual Machine Administrator Login | VM vm-cm02avdd0007 | Operate the data-load VM |

### 4b. Backend app identity (UAI uai-aci-pull-digitalmfg): data plane

The backend and MCP Container Apps authenticate as this UAI (AZURE_CLIENT_ID).

| Role | Scope | Purpose | How assigned |
| --- | --- | --- | --- |
| Cognitive Services User | aif-foundry | Call Foundry models and create/run agents | already present / reuse-rbac.bicep |
| Search Index Data Contributor | srch-foundry | Read/write the RAG search indexes | already present / reuse-rbac.bicep |
| Search Service Contributor | srch-foundry | Manage index definitions | already present / reuse-rbac.bicep |
| Storage Blob Data Contributor | stfoundry | Read/write the dataset blobs | already present / reuse-rbac.bicep |
| Cosmos DB Built-in Data Contributor (00000000-...-0002) | cosmos-foundry (scope /) | Plan/step history read/write | already present (az cosmosdb sql role assignment) |
| AcrPull | acrdigitalmfgrpsidweu01 | Pull the backend/MCP/frontend images | already present |

Note: because the UAI already held every required control-plane and data-plane role from the prior deployment into this landing zone, the reuse-rbac module was effectively redundant and the RBAC pass was skipped.

### 4c. Also attached to the VM

The same UAI was attached to the VM to give it a login identity (see Blocker #3), plus Contributor on rg-gen-digitalmfg and Reader on rg-core-foundry.

## 5. Step-by-step: what was done (in sequence)

### Step 1: Authenticate (laptop)

az login --tenant fe9c207f-da30-4226-82b5-bff6ef031c8c
az account set --subscription cf397678-b660-4714-bea3-5e5b7748bce2

### Step 2: Build & validate the template

az bicep build --file infra/main_reuse.bicep

The template provisions three internal Container Apps plus the Cosmos database/container via gated modules; RBAC is behind a deployRbac parameter.

### Step 3: Build the container images into ACR

The three images were built server-side in the reused Premium ACR (base images are public):

az acr build --registry acrdigitalmfgrpsidweu01 --image macae-backend:reuse-1 --file src/backend/Dockerfile.reuse src/backend
az acr build --registry acrdigitalmfgrpsidweu01 --image macae-mcp:reuse-1 --file src/mcp_server/Dockerfile.reuse src/mcp_server
az acr build --registry acrdigitalmfgrpsidweu01 --image macae-frontend:reuse-1 --file src/App/Dockerfile.reuse src/App

Two build-time adjustments were required (see Blockers #4 and #5): the frontend Dockerfile bumped Node 18 -> 22 for the Vite 7 build, and all Dockerfiles dropped RUN --mount=type=cache because the classic ACR builder has no BuildKit.

### Step 4: Deploy base resources (RBAC off)

deployRbac=false because the UAI already carries the required roles.

az deployment group create `
  --name macae-reuse `
  --resource-group rg-gen-digitalmfg-rpsi-dev-weu-01 `
  --template-file infra/main_reuse.bicep `
  --parameters @infra/main_reuse.parameters.json deployRbac=false

Result: the three Container Apps and the Cosmos macae database/memory container were created.

### Step 5: Resolve container start-up failures

Two apps initially reported ActivationFailed and were corrected without new infra (see Blockers #6 and #7): the backend needed empty APPLICATIONINSIGHTS_CONNECTION_STRING / APPLICATIONINSIGHTS_INSTRUMENTATION_KEY env vars (monitoring is off), and the MCP image CMD was changed to launch python mcp_server.py directly instead of uv run, which re-synced at start-up and never bound port 9000 under the non-root user.

### Step 6: Give the VM a login identity (Conditional Access blocked interactive login)

Interactive/device-code login on the VM was blocked by Conditional Access. Instead the backend UAI was attached to the VM, and on the VM:

az login --identity --client-id 38ab20d0-2349-4503-b63a-4152af0b90ed

### Step 7: Fix Container App reachability from the VM (ingress model)

On an internal Container Apps Environment the ingress model matters: an external=true FQDN resolves (even inside the environment) to a public IP that other containers cannot reach, while an internal FQDN resolves to the environment load balancer 10.22.144.170. The correct model is that only the browser-facing frontend is external; the backend and MCP tool server are internal (see Blockers #8 and #9). After that change the VM browser reaches the frontend through a hosts-file entry that maps its FQDN to 10.22.144.170.

### Step 8: Make the app reachable from the VM (hosts file for private FQDNs)

The subscription has no private DNS zone for the CAE domain and corp DNS has no record for it. A temporary hosts-file entry on the VM maps the private IP to the frontend FQDN:

10.22.144.170   ca-macae-fe-rpsi-dev-weu-01.purplebay-8719396f.westeurope.azurecontainerapps.io

### Step 9: Post-deploy data load (from the VM)

The data loader was run from the VM against the reused Storage, Search, and the backend team-config upload endpoint. It uploads the datasets to blob storage, builds the Search indexes, and posts the agent-team configurations to the backend:

# Repo cloned on the VM
pwsh ./infra/scripts/Load-ReuseData.ps1 `
  -BackendUrl https://ca-macae-be-rpsi-dev-weu-01.purplebay-8719396f.westeurope.azurecontainerapps.io

The loader was hardened for Windows PowerShell 5.1 on the VM (see Blocker #10): ternary expressions rewritten to if/else, non-ASCII dashes stripped, managed-identity principal-id fallback when signed-in-user lookup fails, native-stderr handling, real-Python detection over the Store alias, and az storage container create before upload-batch.

The agent-team JSON files originally referenced models not deployed in this landing zone (gpt-4.1-mini x17 and o4-mini x1); all references were repointed to gpt-5-mini so the uploads succeed (see Blocker #2).

Results:
- Team configs 5/5 uploaded (200): HR, Marketing, RFP Analysis, Contract Compliance, Retail.
- 8 blob containers created and populated; 8 Search indexes built (RFP summary/risk/compliance, Contract summary/risk/compliance, Retail customer 11 files, Retail order 6 files). All Succeeded, 0 Failed.
- Backend health path is /healthz; team upload endpoint is /api/v4/upload_team_config.

### Step 10: Fix task submission (model temperature)

Submitting a task returned 400 'Unable to create plan'. Foundry rejected the temperature parameter because the gpt-5 family (reasoning + chat) does not support it (see Blockers #11 and #12). The agent template was changed to omit temperature for all gpt-5* and o-series models:

Added _model_supports_temperature(model_deployment_name) in foundry_agent.py, returning False for o1/o3/o4 and all gpt-5* deployments.

When temperature is unsupported it is left unset (None) on the chat options.

Rebuilt and redeployed as macae-backend:reuse-2, then reuse-3.

### Step 11: Fix task submission (stale server-side agent version)

After the temperature change the client logs showed temperature being omitted, yet Foundry still returned the same 400. Root cause: Foundry agents are persistent and store their model settings server-side; the agent client reuses the latest stored agent version, which had been created by an earlier build with temperature baked in, so client-side changes never took effect (see Blocker #13). The fix purges the stale agent once per process using the container's managed identity, which forces a fresh, temperature-free version:

Added _purge_stale_server_agent(project_client, agent_name, logger) in foundry_agent.py, calling project_client.agents.delete.

Guarded by a _purged_agent_names set and an asyncio.Lock so the purge runs at most once per agent per process.

Called on the MCP path in _after_open(); ResourceNotFoundError is treated as already-clean.

Rebuilt and redeployed as macae-backend:reuse-4; backend revision went Healthy.

Task submission now passes the responsible-AI check, generates a plan, runs the agents, and persists plan/step history in Cosmos DB.

### Step 12: Fix agent private-endpoint DNS via /etc/hosts injection

The backend reaches Cosmos DB and Foundry over their private endpoints, but corp DNS does not resolve their privatelink FQDNs and Cosmos public access is Disabled. The proper fix (corp DNS forwarders) was under a change freeze and repointing the VNet DNS was denied by Azure Policy, so the mappings were moved into the backend container:

src/backend/entrypoint.sh appends the EXTRA_HOSTS entries to /etc/hosts, then launches uvicorn.

Dockerfile.reuse sets the wrapper as the entrypoint (uvicorn remains the CMD).

Deployed with the host mappings as an env var:

$hosts = "10.22.144.134 cosmos-foundry-rpsi-dev-weu-01.documents.azure.com;10.22.144.135 cosmos-foundry-rpsi-dev-weu-01-westeurope.documents.azure.com;10.22.144.138 aif-foundry-rpsi-dev-weu-01.services.ai.azure.com;10.22.144.137 aif-foundry-rpsi-dev-weu-01.openai.azure.com;10.22.144.136 aif-foundry-rpsi-dev-weu-01.cognitiveservices.azure.com"
az containerapp update -g rg-gen-digitalmfg-rpsi-dev-weu-01 -n ca-macae-be-rpsi-dev-weu-01 `
  --set-env-vars "EXTRA_HOSTS=$hosts"

Startup logs confirm all mappings are applied before uvicorn starts. Mapping the real FQDN to the private IP (not a raw IP) keeps TLS/SNI valid.

## 6. Blockers & resolutions (full, in order)

| # | Blocker | Category | Resolution |
| --- | --- | --- | --- |
| 1 | Cross-RG deploy needed Contributor + UAA on rg-core-foundry | Permissions | Activated PIM roles; RBAC deploy split into deployRbac=false, RBAC pass skipped (UAI pre-authorized) |
| 2 | Team JSON referenced gpt-4.1-mini/o4-mini; LZ has gpt-5-mini/gpt-5-chat/gpt-5.5 | Config | Repointed all 18 model references to gpt-5-mini |
| 3 | VM interactive/device-code login blocked by Conditional Access | Identity/Policy | Attached UAI to VM; az login --identity |
| 4 | Frontend Vite 7 build fails on Node 18 | Tooling | Bumped the frontend image to Node 22 in Dockerfile.reuse |
| 5 | az acr classic builder has no BuildKit; RUN --mount=type=cache fails | Tooling | Removed the cache-mount lines from all Dockerfiles |
| 6 | Backend ActivationFailed: missing APPLICATIONINSIGHTS_CONNECTION_STRING | App/Config | Added empty APPLICATIONINSIGHTS_CONNECTION_STRING / _INSTRUMENTATION_KEY env vars (monitoring off) |
| 7 | MCP ActivationFailed: uv run re-syncs at start-up, never binds :9000 as non-root | App/Config | Changed the MCP image CMD to run python mcp_server.py directly (venv on PATH) |
| 8 | Apps external=false gave .internal FQDN, unreachable from the peered VM subnet | Network | First set ingress external=true; VM then reached them via env LB 10.22.144.170 |
| 9 | Frontend 500 'No teams available': external FQDN resolves to a public IP the frontend can't reach app-to-app | Network | Corrected model: only the frontend is external; backend + MCP are internal |
| 10 | Data loader breaks on Windows PowerShell 5.1 (ternary, dashes, MI id, stderr, python alias, pip, container) | Tooling | Hardened Load-ReuseData.ps1 for PowerShell 5.1 and managed-identity auth |
| 11 | Task submit 400: gpt-5-mini (reasoning) rejects temperature | Model/Config | Omit temperature for gpt-5* and o-series in foundry_agent.py (reuse-2) |
| 12 | Task submit 400: gpt-5-chat (RAI check) also rejects temperature | Model/Config | Dropped the chat exception so all gpt-5* omit temperature (reuse-3) |
| 13 | Task submit 400 persists: stale server-side agent version replays baked-in temperature | Agent runtime | One-time-per-process agent purge via managed identity forces a fresh version (reuse-4) |
| 14 | Could not delete the stale agent via operator REST (data-plane 403, slow role propagation) | Identity/RBAC | Purged from inside the container using the pre-authorized managed identity |
| 15 | Backend health probe failing against /health | Config | Correct health path is /healthz |
| 16 | Agent calls fail: Cosmos DB and Foundry private endpoints not resolvable, public access Disabled | Private DNS/Network | Resolved via /etc/hosts injection (EXTRA_HOSTS) in the backend image |
| 17 | Corp DNS lacks privatelink records; VNet custom DNS bypasses Azure Private DNS zones | Private DNS/Network | Root cause of #16; permanent fix (corp forwarders) blocked by freeze, bridged by the /etc/hosts fix |
| 18 | Laptop can't resolve *.azurecontainerapps.io (corp DNS NXDOMAIN) | Network | Validate UI from the VM (hosts-file entry to 10.22.144.170) |
| 19 | ACR hardening to public-disabled needs a corp-DNS privatelink.azurecr.io record | Private DNS | Dev-acceptable; left public until the freeze lifts and the DNS record is added |

Outcome: the application works end-to-end. The underlying permanent DNS forwarders (#17) are bridged by the /etc/hosts fix and the ACR hardening (#19) is left dev-acceptable until the freeze lifts.

## 7. The task-submission fix in depth: persistent agents and private-endpoint DNS

Two distinct issues had to be solved before a submitted task could produce a plan.

### 7a. Model temperature and the stale server-side agent

The gpt-5 family (both the reasoning deployment gpt-5-mini and the chat deployment gpt-5-chat) rejects the temperature parameter outright. Omitting it in client code was necessary but not sufficient, because Foundry agents are persistent: their model settings are stored server-side and the agent client reuses the latest stored version. An agent version created by an earlier build still carried temperature, so it kept being replayed. Deleting the agent once per process (using the container's already-authorized managed identity) forces the client to create a fresh, temperature-free version on the next run.

### 7b. Why /etc/hosts, not DNS forwarders

| Approach | Needs on-prem change | Needs VNet write | Blast radius | Reversible | Used? |
| --- | --- | --- | --- | --- | --- |
| Corp DNS forwarders (proper fix) | Yes (frozen) | No | Whole VNet | - | frozen |
| Repoint CAE VNet DNS to a resolver | No | Yes (policy-denied) | Whole VNet | - | blocked |
| /etc/hosts injection in backend image | No | No | Single container | Delete one env var | yes |

Why it works: /etc/hosts is consulted before DNS, so the backend reaches Cosmos DB and Foundry over their private endpoints without asking corp DNS. Mapping the real hostname (not a raw IP) preserves TLS validity. Rollback after the freeze: once corp DNS forwarders exist, remove the EXTRA_HOSTS app setting; no rebuild is needed.

## 8. VM tooling used

| Tool | Purpose |
| --- | --- |
| Azure CLI | Control-plane ops, deployment outputs, az login --identity |
| Windows PowerShell 5.1 | Run the Load-ReuseData.ps1 data loader |
| Python 3 + azure-identity | Blob upload and Search index build within the loader |
| Browser (on the VM) | Validate the frontend at the private FQDN via the hosts-file entry |

## 9. Final status summary

| # | Item | Status |
| --- | --- | --- |
| 1 | Base bicep deploy (3 Container Apps, Cosmos macae DB/container) | Done |
| 2 | RBAC (UAI already carried all required roles) | Done (pre-existing) |
| 3 | Container images built and apps repointed | Done (Healthy) |
| 4 | VM login via attached UAI | Done |
| 5 | Ingress model corrected (frontend external, backend + MCP internal) | Done |
| 6 | Team configs uploaded (5 teams) + Search indexes built (8) | Done |
| 7 | Task submission generates a plan; agents run | Done |
| 8 | Plan/step history persists in Cosmos DB | Done |
| - | Corp DNS forwarders for privatelink zones (remove EXTRA_HOSTS after) | Post-freeze (network team) |
| - | ACR hardening to public-disabled (add privatelink.azurecr.io record) | Post-freeze (network team) |

## 10. Key resource reference

| Resource | Detail |
| --- | --- |
| CAE | cae-foundry-rpsi-dev-weu-01, internal, IP 10.22.144.170, domain purplebay-8719396f.westeurope.azurecontainerapps.io |
| Frontend | ca-macae-fe-rpsi-dev-weu-01, image macae-frontend:reuse-1, external ingress, URL https://ca-macae-fe-rpsi-dev-weu-01.purplebay-8719396f.westeurope.azurecontainerapps.io |
| Backend | ca-macae-be-rpsi-dev-weu-01, image macae-backend:reuse-4, internal ingress (:8000), health /healthz, UAI clientId 38ab20d0-..., principalId 5729970b-... |
| MCP | ca-macae-mcp-rpsi-dev-weu-01, image macae-mcp:reuse-2, internal ingress (:9000) |
| ACR | acrdigitalmfgrpsidweu01.azurecr.io (Premium) |
| Foundry | aif-foundry-rpsi-dev-weu-01, project DigitalManufacturing, endpoint https://aif-foundry-rpsi-dev-weu-01.services.ai.azure.com/api/projects/DigitalManufacturing, PEs .136/.137/.138 |
| Models | gpt-5-mini (agents + reasoning), gpt-5-chat (responsible-AI check), gpt-5.5, text-embedding-3-large |
| Search | srch-foundry-rpsi-dev-weu-01 (connection srchfoundryrpsidevweuz7toiu), PE 10.22.144.133 |
| Storage | stfoundryrpsidweu01 (public Disabled + Deny), blob-PE 10.22.144.132 |
| Cosmos | cosmos-foundry-rpsi-dev-weu-01 (public Disabled), db macae / container memory (partition /session_id), PEs 10.22.144.134/.135 |
| VM | vm-cm02avdd0007 (Windows 11 multi-session / AVD), IP 10.22.120.68, subnet snet-vm (vnet-shared) |
| Agent teams | HR, Marketing, RFP Analysis, Contract Compliance, Retail (all on gpt-5-mini) |